## TODO
Datum	eff. Prio	Prio	Time	Art	Where	Description
2014-04-05	6	6	1	Todo	ToolWindow	intercept green 'maximize' button
2013-12-31	2.25	9	4	Bug	Tape	TC2068: Instant Tape Save/Load does not work
2012-08-15	2	8	4	Todo	File	.Z80: ROM laden, speichern
2014-03-29	2	4	2	Todo	Debugger	DisassView: edit asm: catch <tab> and go from instr -> args field
2012-08-21	1.75	7	4	Todo	Settings	key_save_and_restore_session
2012-12-12	1.5	6	4	Todo	Debugger	Graphical Inspector: alle register highlighten
2012-12-12	1.5	6	4	Todo	Debugger	Memory Access Inspector: alle register highlighten
2012-12-08	1.3333333333	4	3	Todo	Debugger	Graphical Inspector: Knopf "2x2"
2012-12-08	1.25	5	4	Todo	Debugger	Memory Access Inspector: export "ranges" Datei
2013-01-07	1	4	4	Todo	Debugger	Graphical View: 2x2 Mode
2013-01-07	1	4	4	Todo	Debugger	Disass View: Show Tooltip with Register over Hex View
2013-01-07	1	4	4	Todo	Debugger	Disass View and Hex View: link cursor rows in l & r view
2013-06-12	1	4	4	Todo	Z80	bits 3 and 5 in F register in opcodes not using zlog_flags[]
2014-03-29	1	4	4	Todo	Debugger	Option: display dec/hex, assume input data in addr lineedit is dec/hex without prefix
2014-04-05	1	4	4	Todo	Z80	Z80 Inspector: button: reset speed to 100%
2015-04-19	1	3	3	Todo	Tape	Menu>Option>Muffle tape-out (switch on/off tape noise)
2013-11-24	0.75	9	12	Bug	TC2068	TS2068 crashes for unknown reason, e.g. on SAVE "x"
2012-10-24	0.75	6	8	Todo	MMU	TS1500: Mmu
2012-08-22	0.75	3	4	Todo	Settings	key_use_individual_settings
2014-03-20	0.75	6	8	Todo	DivIDE	show DivIDE and IDE registers
2012-12-12	0.6666666667	4	6	Todo	Debugger	Hex Inspector: drag to select range
2012-12-09	0.6666666667	2	3	Todo	Debugger	Memory Inspectors: "Back" Button
2012-08-15	0.625	5	8	Todo	AY	Zonx Box + Didaktik Melodik Controls
2012-12-01	0.625	5	8	Todo	Audio	support samples per sec: audioin != audioout
2012-12-08	0.625	5	8	Todo	Debugger	DisassView: import "ranges+labels" Datei
2013-11-24	0.625	5	8	Todo	zasm	load .dck files from .ass source
2012-06-13	0.5833333333	7	12	Todo	Inspector	SPECTRA Interface Inspector: register display & edit
2012-10-23	0.5	4	8	Todo	Inves	Inves: emulate the "and-mask" effect of bytes written to "rom"
2012-12-01	0.5	4	8	Todo	Audio	audio in selector. STOPPER: unterschiedl. samples/sec für audio in und out
2013-06-05	0.5	4	8	Todo	Screen	einige ZX81 Grafik-Demos funktionieren nicht
2012-08-21	0.5	2	4	Todo	Keyboard	handle caps lock in "Physical" mode. "Basic" mode probably ok, Qt::Key_CapsLock.
2012-08-23	0.5	2	4	Todo	ULA	Ula: Eingaben in ULA Inspector
2012-08-25	0.5	2	4	Todo	ZXSP	zxsp: Crtc und Mmu Werte ändern
2012-08-25	0.5	2	4	Todo	ZXSP128	zx128: Crtc und Mmu: Werte ändern
2012-08-25	0.5	2	4	Todo	ZX+3	zxplus3: Crtc und Mmu Werte ändern
2013-10-16	0.5	2	4	Todo	Tape	TS2020 Tape Info unter Deckel zeichnen
2013-10-19	0.5	2	4	Todo	Lenslok	Game-Titel im Lenslok eingeprägt anzeigen
2015-04-19	0.5	1	2	Todo	Tape	save Jupiter Ace .tap files in Jupiter Ace flavour
2012-08-19	0.4166666667	5	12	Todo	Crtc, Mmu	Crtc und Mmu für andere Versionen: Werte anzeigen
2013-10-23	0.4166666667	5	12	Todo	Debugger	assembler listing für disassembler nutzen
2013-10-21	0.4	4	10	Todo	Screen	Video Beam Indicator for b&w machines (zx80/81/jupiter)
2013-06-05	0.375	6	16	Todo	Screen	TC2048 64 Column Mode: smooth downscaling for zoom=1
2012-09-30	0.375	3	8	Todo	Item	Stonechip 16k auf 32k Erweiterung
2014-03-20	0.3333333333	6	18	New	Debugger	automate adding/removing of memory: DivIDE, Spectra, TCC
2012-12-12	0.3333333333	4	12	Todo	Debugger	Hex Inspector: Undo
2012-08-18	0.3	6	20	New	Plus 2A	Printer: +2A
2013-06-11	0.3	6	20	Todo	Spectra	SPECTRA Interface: RS232
2012-08-15	0.25	5	20	Todo	TZX	TZX als Audio speichern
2013-10-10	0.25	2	8	Todo	Tape	TS2020 Achsen
2013-11-24	0.25	2	8	Todo	TC2068	individual upper-side labels for Timex cartridges
2014-03-20	0.25	4	16	New	DivIDE	insert /dev/disk* (incl. suid helper process)
2016-02-27	0.25	2	8	New	SPECTRA	Support new +128k support
2012-08-15	0.2	4	20	New	Debugger	Memory komplett disassemblieren
2012-10-26	0.2	4	20	Todo	Jupiter	Jupiter Ace: memory access priority (and waitstates) depending on address range
2014-03-24	0.2	3	15	Todo	DivIDE	simulate Flash Eeprom writing
2013-11-24	0.15	3	20	Todo	U2086	Printer port
2016-02-15	0.125	5	40	New	Pentagon	Pentagon 128 FDC
2016-02-27	0.1	2	20	Todo	Memory	waitmap-Daten sollten am Memory hängen, da es ein Attribut des jeweiligen Speichers ist
2014-03-27	0.0833333333	1	12	Todo	DivIDE	2nd Drive
2012-10-24	0.0808080808	8	99	Todo	TK85	TK85: joystick: STOPPER: port address and data bits
2014-04-05	0.0202020202	2	99	Todo	+3 span	side view image with joystick ports
2017-11-11	0.1333333333	4	30	New	Tape	save tape as audio
2017-11-11	0.4	4	10	Bug	Keyboard	check compound key decomposition/animation
2017-11-11	0.5	5	10	Bug	Tape	tape recorder button animation
2017-11-11	0.2666666667	4	15	Todo	Disk	speedup: Disk Drive auch beschleunigen
2017-11-14						dialog config kbd joystick can be opened more than once
2018-06-09	2	4	2	Crash	TZX	uni/audio/tzx-data:2351: assert(phase0==0) not neccessarily true

Hours:			796

New Items:
2012-08-18	0.4	8	20	New	Item	ZX Interface 1
2012-08-18	0.4	8	20	New	Item	Printer: ZxPrinter
2012-08-18	0.2	4	20	New	Item	Printer: TS2040
2012-08-15	0.125	1	8	New	Item	Fuller Box
2012-08-18	0.1	2	20	New	Item	Printer: Lprint III
2012-08-18	0.15	6	40	New	Item	FdcBeta128
2012-08-18	0.05	2	40	New	Item	FdcD80
2012-08-26	0.05	1	20	New	Item	num. keypad 128
2012-08-18	0	0	40	New	Item	FdcJLO
2012-08-19	0	0	20	New	Item	Printer: Aerco
2015-05-18	0.125	1	8	New	Item	Cheetah R.A.T

New Machines:
2012-09-19	0.0125	1	80	New	Machine	Spectrum SE
2013-06-16	0.125	1	8	New	Machine	NTSC Spectrum --> http://scratchpad.wikia.com/wiki/NTSC_Spectrum

New Feature:
2012-09-25	1.25	5	4	New	App	Log Window
2012-08-25	0.125	1	8	New	File	AY-File abspielen
2012-08-19	0.075	3	40	New	App	Soziale Funktionen: über Netz 2 Maschinen syncen, chatten, Termine vereinbaren
2012-08-19	0.05	2	40	New	Machine	2 Maschinen synchronisieren
2013-06-13	0.2	8	40	New	File	New File Format: SZX
2013-09-14	0.025	1	40	New	File	File format ".FDI" (TR-DOS, ß-Disk)
2013-09-14	0.025	1	40	New	File	File format ".TRD" (TR-DOS, ß-Disk)
2013-09-14	0.025	1	40	New	File	File format ".IMG" (+D)
2013-09-14	0.025	1	40	New	File	File format ".MGT" (+D)

Canceled:
2012-08-21	0	0	4	New	Menu	Tooltips anzeigen
2013-01-07	0.5	8	16	Todo	Qt	G4/G5 Version

## Done
When	eff. Prio	Prio	Time	Type	Where	Description
2012-08-16	5	5	1	Fail	Machine	Inves does not boot
2012-08-18	4	4	1	New	Machine	PowerOffOn: Zeit resetten
2012-08-19	1	3	3	Bug	Keyboard	Tastatureingaben werden ignoriert wenn Kbd Inspector im Vdgr
2012-08-19	3	6	2	Bug	Keyboard	Rechtsklick in Keyboard wird als Tastendruck "erkannt"
2012-08-19	2.3333333333	7	3	New	App	Open App with File
2012-08-20	3.5	7	2	Bug	Kbd	Symbol Shift Sticky funzt nicht
2012-08-20	2.25	9	4	Bug	Tastatur	ModifierKeys werden nicht gesehen
2012-08-20	2	8	4	New	Screen	Screen auf 2. Thread rendern
2012-08-21	2.5	5	2	Bug	Inspector	Inspectors funktionieren nicht mehr nach neuer Maschine
2012-08-21	1.75	7	4	New	Prefs	Letztes Machine-Model merken
2012-08-21	1.5	3	2	New	Prefs	Fensterpositionen merken
2012-08-22	1.25	5	4	New	Prefs	AY und JOY prefs beachten
2012-08-22	0.6666666667	2	3	New	Inspector	nach newMachine Item mit selber Klasse (nicht nur exakt gleiche ID) suchen
2012-08-22	0.75	9	12	New	Prefs	Preferences Inspector
2012-08-22	9	9	1	New	Prefs	key_snapshot_keyboard_mode
2012-08-22	9	9	1	New	Prefs	key_startup_keyboard_mode
2012-08-23	8	8	1	New	Prefs	key_startup_fullscreen
2012-08-23	5	5	1	New	Prefs	key_startup_enable_audio_input
2012-08-23	2.5	5	2	New	Prefs	key_audio_playthrough_damping
2012-08-25	1.75	7	4	New	Inspector	Crtc und Mmu für zxsp: Werte anzeigen
2012-08-25	1.75	7	4	New	Inspector	Crtc und Mmu für zx128: Werte anzeigen
2012-08-25	1.75	7	4	New	Inspector	Crtc und Mmu für zxplus3: Werte anzeigen
2012-08-25	1.5	3	2	New	Prefs	key_leave_keyboard_open
2012-08-25	1.5	3	2	New	Prefs	key_leave_taperecorder_open
2012-08-26	2.25	9	4	New	Item	class TapeRecorder : public Item
2012-09-03	1.3333333333	4	3	Impr	Screen	OpenGL-Output: weniger Blocks
2012-09-09	0.45	9	20	New	Tape	Tap File als Audiofile
2012-09-09	2.5	5	2	Bug	Tape	Block info wechselt nicht korrekt
2012-09-09	2.25	9	4	New	Tape	internal Tape Recorder
2012-09-11	4.5	9	2	ToDo	Machine	close inspector => remove checkmark in items_menu
2012-09-12	1	4	4	New	Joystick	Protek Joystick
2012-09-13	2.5	5	2	Test	Joystick	Protek/Cursor Joystick Interface
2012-09-13	4.5	9	2	Test	Joystick	Sinclair Joystick Interface
2012-09-13	1.25	5	4	Neu	Joystick	dk'tronic Dual Joystick Interface
2012-09-16	0.625	5	8	New	Item	Interface 2
2012-09-17	1	4	4	New	Item	Ram_Erweiterung für ZXSP 16k
2012-09-18	1.5	9	6	New	App	Check Update
2012-09-19	4.5	9	2	New	Prefs	key_check_for_update, key_check_for_preview
2012-09-19	0.5	4	8	Fail	SNA	MyStory.sna und Blackbeard.sna starten nicht: PC 2x gepoppt.
2012-09-19	2.25	9	4	New	Screen	save gif image
2012-09-19	2	8	4	New	Screen	save gif movie
2012-09-20	1	8	8	New	Machine	Jupiter
2012-09-20	0.75	3	4	New	Item	Jupiter: 16k Ram Extension
2012-09-24	1.125	9	8	New	Tape	TZX als Audio laden
2012-09-24	2.5	5	2	Todo	Tape	Tzx-File: block start polarity: Checked
2012-09-25	8	8	1	Todo	Keyboard	Key Focus nach Menü oder File Requester
2012-09-27	2	8	4	New	Tape	fast load
2012-09-28	2.6666666667	8	3	Todo	Tape	Fast Load auch bei laufendem Tape
2012-09-28	0.625	5	8	New	Tape	key_auto_start_stop_tape
2012-09-28	4	8	2	Todo	Tape	Fast Load Preferences Option
2012-09-29	1	8	8	New	Machine	ZX80
2012-09-29	1	8	8	New	Machine	ZX81
2012-09-29	0.4	8	20	New	Crtc	Crtc ZX80
2012-09-29	0.4	8	20	New	Crtc	Crtc ZX81
2012-09-30	1.25	5	4	New	Item	ZX 16K, TS1016, Stonechip 16k, Memopak 16k
2012-09-30	2	8	4	New	Item	ZX 1-3k Ram
2012-09-30	8	8	1	New	Prefs	always_attach_ram_extension
2012-09-30	2	8	4	New	Item	ZX 1-3k Ram Inspector
2012-09-30	1	8	8	New	Item	Memopak 64k
2012-10-01	1.8	9	5	Bug	Z80	ZX80/81: leerer Screen wenn Screen nicht in $C000++ gespiegelt
2012-10-02	4.5	9	2	Todo	Z80	HALT und IRPT --> Macro PEEK_INSTR(R)
2012-10-02	2.25	9	4	New	Item	Memopak 64k Inspector
2012-10-03	4	8	2	Todo	Tape	ZX80 instant load
2012-10-04	4	8	2	Todo	Tape	ZX81 instant load
2012-10-06	1.25	5	4	Todo	Machine	MachineController.showMachineImage()
2012-10-07	1.75	7	4	Bug	Inspector	Re-use of toolwindows after machine change does no longer work
2012-10-07	2.25	9	4	Todo	File	Save Snapshot as: sna, z80, scr, rom, p, o, 80, 81
2012-10-07	1.75	7	4	Todo	Prefs	save and restore MainWindow and ToolWindow positions
2012-10-10	2.5	5	2	Todo	File	load ZX80 snapshot from .o or .80 file
2012-10-10	1.5	6	4	Todo	File	load ZX81 snapshot from .p, .81 or .p81 file
2012-10-16	0.5	5	10	Todo	Qt	Management of ToolWindows reworked
2012-10-16	1	1	1	Todo	Project	reworked hierarchy: Qt/, Mac/, Uni/
2012-10-17	1.5	6	4	Todo	App	Splashscreen after open without snapshot
2012-10-17	2	4	2	Todo	Prefs	key_startup_open_machine_image
2012-10-17	4.5	9	2	Todo	File	.z80 load&save: ZX80, ZX81 und JupAce testen
2012-10-17	4	8	2	Crash	App	Fixed crash at quit after access to dsp lock
2012-10-17			327			released 0.8.0pre6
2012-10-18	4	8	2	Crash	App	Crash when starting zxsp with double click on snapshot file
2012-10-21	1	4	4	Todo	App	move Item showActions into window_menu
2012-10-21	1	4	4	Todo	App	window_menu: QActionGroup for zoom 1…4 and fullscreen
2012-10-22	5	5	1	Todo	Inspector	select Stereo mix in AY inspector, checked mix for misc. devices
2012-10-22	2	8	4	Todo	Debugger	Cpu: halt, step-in, step-over, step-out
2012-10-22	0.5	2	4	Todo	Inspector	Eingaben im AY Inspector
2012-10-24	1	4	4	New	Machine	Enabled TS1000, TS1500, TK85, TC2048 and TK90X, all still work needing
2012-10-24	0.5	4	8	Todo	Kbd	Tk85: keyboard image
2012-10-24	0.5	4	8	Todo	Machine	TK90X: kbd image
2012-10-24	0.25	2	8	Todo	Inspector	TS1000: machine image, kbd image
2012-10-24	0.25	2	8	Todo	Machine	TS1500: machine image, kbd image
2012-10-24	1	8	8	Todo	Screen	Screens of newly added ZX80 clones do not work
2012-10-26	3	6	2	Todo	Machine	ZX80: pref for 50/60 Hz
2012-10-26	3	6	2	Todo	Machine	JupAce: 50/60 Hz switch: preferences
2012-10-27	2	6	3	Todo	Kbd	TK90X: Keyboard
2012-10-27	2	6	3	Todo	Kbd	TS1000: Keyboard
2012-10-27	2	6	3	Todo	Kbd	TS1500: Keyboard
2012-10-27	2	6	3	Todo	Kbd	TK85: Keyboard
2012-10-27	4	8	2	Todo	Joy	TK90X and TK95: joystick: port, subclass, inspector
2012-10-27	1	8	8	Todo	Joy	TK85: joystick: port, subclass, inspector
2012-10-27			89			released 0.8.0pre7
2012-10-29	2.25	9	4	Todo	Debugger	CPU: Eingaben in CPU Inspector
2012-08-17	0.45	9	20	New	Debugger	Mem: Memory Dump anzeigen: Bytes
2012-11-17			24			released 0.8.0pre8
2012-11-19	2.25	9	4	New	Debugger	Mem: Memory Dump anzeigen: Words
2012-11-20	1.125	9	8	New	Debugger	Mem: Memory Dump anzeigen: Disass
2012-11-21	0.75	9	12	New	Debugger	Mem: Memory Dump anzeigen: Grafisch
2012-11-22	1.25	5	4	Todo	Z80	Umstellung auf 32-bit CoreBytes
2012-11-25	0.75	9	12	New	Debugger	Mem: Memory Dump anzeigen: Access
2012-11-30	9	9	1	Todo	Audio	Audio-in enablen
2012-12-01	4	4	1	Todo	Audio	Play-through eliminiert
2012-12-02	0.5	6	12	Todo	Debugger	Memory View: unified header widget
2012-12-07	1.125	9	8	Todo	Debugger	Mem: Memory Dump anzeigen: Bytes+Words
2012-12-07			62			released 0.8.0pre9
2012-12-08	5	5	1	Todo	Debugger	DisassView: highlight opcode under pc
2012-12-09	2.5	5	2	Todo	Debugger	DisassView: indicate breakpoint positions: RGB in HexView
2012-12-09	2.5	5	2	Todo	Debugger	HexView: indicate breakpoint positions
2012-12-09	2.5	5	2	Todo	Debugger	HexView: highlight opcode under pc
2012-12-09	5	5	1	Todo	Inspector	Ula Inspector: don't show contended ram details if no contended ram exists
2012-12-09	8	8	1	Todo	TC2048	no addAction found for item TC2048 Joystick Port
2012-12-09	5	5	1	Todo	Debugger	MemoryHexInspector: save prefs when switching model
2012-12-09	2.5	5	2	Todo	Debugger	HexView: Tooltips
2012-12-10	1.25	5	4	Todo	Debugger	HexView: set/clear rwx breakpoint
2012-12-11	2	8	4	Todo	Debugger	HexView: Edit memory
2012-12-12	4.5	9	2	Todo	Debugger	CPU: break on breakpoints
2012-12-12	8	8	1	Todo	Debugger	Hex Inspector: on key: force edit pos inside window
2012-12-12	3	6	2	Todo	Debugger	Hex Inspector: highlight all registers
2012-12-12	8	8	1	Bug	Debugger	CPU Inspector: run up to cycle: update cc display despite of keyboard focus
2012-12-12	0.8333333333	5	6	Todo	Debugger	Disass Inspector: set/clear breakpoint
2012-12-14	2.5	5	2	Todo	Debugger	Disass Inspector: Aufsetzpositionen nach Scrollen
2012-12-16	0.5	2	4	Todo	Debugger	Disass Inspector: alle register highlighten
2012-12-22			38			released 0.8.0pre10
2012-12-29	1.25	5	4	Todo	Debugger	Disass Inspector: Highlight view and blink cursor if keyboard focus
2012-12-29	1.25	5	4	Todo	Debugger	Hex Inspector: Highlight view and blink cursor if keyboard focus
2012-12-29	1.75	7	4	Todo	Debugger	Hex Inspector: Edit Ascii
2013-01-02	0.75	6	8	Todo	Debugger	Disass Inspector: edit opcode
2013-01-12			20			released 0.8.0pre11
2012-09-09	0.15	6	40	Todo	Tape	tape animation and click animationen in TapeView
2013-05-12	4	8	2	Todo	Tape	Context menu: insert new empty tape
2013-05-20			42			released 0.8.0pre13
2012-10-24	0.5	8	16	Todo	TC2048	TC2048: Mmu
2013-05-12	2.25	9	4	Crash	Screen	ULA: update border -> NULL pointer
2013-05-30	2	8	4	Todo	TC2048	TC2048: save & load .z80
2012-08-15	0.4	8	20	New	TC2048	TC2048: Screen
2013-05-30			44			released 0.8.0pre14
2013-06-01	1	8	8	Todo	Screen	ScreenZxsp: reimplement screenshot, record movie
2013-06-01	0.625	5	8	Todo	Screen	ScreenTc2048: screenshot, record movie
2012-08-26	1.5	6	4	Todo	Screen	ScreenMono: angezeigten Müll im Border fixen
2012-09-21	1.25	5	4	Todo	Screen	ScreenMono: screenshot, record movie
2012-08-26	2	8	4	Bug	ZX80	ZX80 @ 60Hz: die obersten 3 Zeilen werden nie (erfolgreich) angezeigt. Border?
2013-06-01	1	4	4	Todo	Screen	Gif Movies mit und ohne Border-Animation
2013-06-06			32			released 0.8.0pre15
2013-06-05	3	6	2	Todo	AY	AY-Magic durch Didaktik ersetzen
2012-09-19	0.25	5	20	New	Item	SPECTRA Interface: display modes
2013-06-11	0.5	5	10	Todo	Item	SPECTRA Interface: external rom, joystick
2013-06-12	4	4	1	Todo	CPU	added bits 3 and 5 to zlog_flags[]
2013-06-11	2.25	9	4	Todo	Item	SPECTRA Interface: GIF screenshot
2013-06-11	2.25	9	4	Todo	Item	SPECTRA Interface: flashing border
2013-06-11	0.8	8	10	Todo	Item	SPECTRA Interface: double buffered ram
2013-06-14	1.25	5	4	Todo	Files	SPECTRA Interface: .z80 file support
2013-06-11	4.5	9	2	Crash	Inspector	new empty Inspector Window -> select item in context menu -> crash
2013-06-15			57			released 0.8.0pre16
2013-06-17	2	6	3	Bug	Item	Spectra: Enhanced border extra colours: wrong colours
2013-06-17	2.6666666667	8	3	Bug	File	Spectra: load .z80 file: some bug fixes
2013-06-18	4.5	9	2	Bug	Z80	wait cycles sometimes added when they shouldn't (-> Spectra + Shock Part II)
2013-06-18	1.5	6	4	New	Machine	Multiple instances
2013-06-18			12			released 0.8.0pre17
2012-09-30	0.1	8	80	New	Machine	Sinclair +3 (incl. Fdc 765)
2013-09-10			80			released 0.8.0pre18
2013-09-12	4	8	2	Crash	Tape	insert empty .tzx file crashes
2012-10-18	1.75	7	4	Todo	Jupiter	.TAP: Jupiter ACE load
2012-10-10	1	4	4	Todo	Jupiter	Jup Ace: instant load
2013-09-16	1	2	2	Todo	Keyboard	Graphics mode (CAPS SHIFT + 9) could not be invoked in BASIC kbd mode
2013-09-14	0.25	3	12	New	File	Jupiter Ace: File format "Ace"
2012-12-22	1	8	8	Todo	Qt	Move to 5.0.0
2013-10-01	0.125	5	40	New	Tape	TS2020
2013-10-10			72			released 0.8.0pre19
2013-10-11	0.1	4	40	New	Item	Lenslok
2013-10-10			40			released 0.8.0pre20
2012-12-09	0.6	6	10	Todo	Screen	Video Beam Indicator for color machines
2012-08-15	1.125	9	8	Todo	File	Assembler source laden
2013-10-23	9	9	1	Bug	Files	save .ACE: forgotten final $ED00
2013-10-23	1.5	6	4	Todo	Assembler	#target ace
2013-10-23	9	9	1	Crash	Files	load .ACE: adding and immediately removing rampack crashed in the queued signal_item_attached
2013-10-23	1	8	8	Todo	Assembler	#target z80
2013-10-23	2	8	4	Todo	File	.rom laden
2013-10-23	1	4	4	Todo	File	.rom ggf. in IF2 oder Spectra IF laden
2012-08-15	2	8	4	Todo	ZXSP	SCR laden
2013-10-29	4	4	1	Todo	File	added model ZXPlus, TK85, TK90X and TK95 to .z80 file spec
2012-08-15	1	8	8	Todo	File	load .tap file as snapshot
2013-10-29	2	8	4	Todo	File	load .dsk file as snapshot
2012-10-27	1	4	4	Todo	ZX80++	ULA b&w machines: display parameter anzeigen
2012-06-16	1	8	8	Todo	TK90X	TK90X and TK95: 60 Hz Model
2013-10-30	2	8	4	Todo	TK85	TK85: 60 Hz Model
2013-11-01	1.125	9	8	Crash	Screen	long haunting bug: crash when double releasing Screen::_mutex
2013-11-01			81			released 0.8.0pre21
2012-10-24	4	8	2	Todo	TK95	TK95: joystick inspector image
2013-11-01	2	8	4	Todo	TK95	TK95: keyboard image
2013-11-01	2	4	2	Todo	Spectra	recent files in context menu
2013-11-01	2	4	2	Todo	IF2	recent files in context menu
2012-08-19	0.1	8	80	New	Machine	TC2068, TS2068, U2086
2013-11-23			90			released 0.8.0pre22
2012-09-20	0.1	8	80	New	Item	DivIDE
2014-03-20	8	8	1	Bug	File	Open File Requester ignores setDirectory etc.: work around Qt Bug
2014-02-01	4	8	2	Bug	Qt	OpenFileSelector returns folder "*.tzx" instead of stepping into it
2014-03-20	0.25	2	8	New	File	File format ".HDF" (DivIDE)
2014-03-20	1.5	9	6	Bug	MMU	handle ROMCS in models with paged memory properly, e.g. for DivIDE
2012-12-08	2	8	4	New	Debugger	Disass Inspector: follow pc
2014-03-28	2	8	4	Bug	Debugger	setting breakpoint in DisassView sometimes corrupts data
2014-03-29	1.5	6	4	Bug	Debugger	PC coloring in DisassView broken
2014-03-13	2	8	4	Bug	Keyboard	+A +shift -shift -> key A also released
2014-04-01			113			released 0.8.0pre23
2014-04-02	3	6	2	Crash	Files	TC2068 -> reload *.hdf -> crash
2012-10-18	1	4	4	Todo	Qt	Qt-Abhängigkeit in Uni eliminieren: Item.Kbd
2014-03-13	2	8	4	Bug	Keyboard	128++ Compound Keys werden nicht mehr korrekt dekodiert und visualisiert
2014-04-03	2	4	2	Todo	Keyboard	Key mapping überarbeitet. ESC -> SHIFT+SPACE usw.
2012-08-20	1	4	4	Todo	Keyboard	ZX80/81 keyboard vs. ZXSP keyboard: managed in Keyboard c'tor
2013-11-21	2.25	9	4	Crash	Machine	load 2++ files in one go (e.g. dbl clicking) => crash
2014-04-10	9	9	1	Crash	Joysticks	scanning USB bus for joysticks crashed for each joystick found
2014-04-10	2	4	2	Bug	TS2068	joysticks swapped, fire button wrong bit (bugger, WoS!)
2014-04-10	9	9	1	New	Domain	changed update url to k1.spdns.de
2014-04-11	3	3	1	Bug	Joysticks	opening Joystick Inspector reassigned joysticks
2014-04-11			25			released 0.8.0pre24
2014-04-12	3	3	1	Todo	Debugger	fast clicks in scrollbar should be handled as normal and not ignored as double clicks
2014-04-12	0.3	6	20	Todo	Debugger	use QToolBar for buttons
2014-04-05	2	4	2	Todo	Keyboard	get double click mouse button event -> normal next click
2012-08-19	1	3	3	Todo	Keyboard	ctrl-click im Kbd abfangen -> symbolshift + Taste
2014-04-17	2	8	4	Bug	Mouse	Kempston MIF: Mouse grabbing & tracking did no longer work in Qt 5.x
2015-04-04	1	3	3	Bug	Audio	fixed audio interrupt drop-outs (thanks, Apple!)
2015-04-04	2	8	4	Bug	Qt	fixed paintEvent() issue for Qt 5.4 (thanks, Qt!)
2015-04-07	1	5	5	Bug	Audio	investigated regular x-long irpt runtime: WLAN-internet bridge! (thanks, Apple!)
2015-04-08	0.3	3	10	Todo	Logfile	new logging module: log to file in /var/log or /tmp
2015-04-09	1.5	6	4	Todo	Audio	menu option "enable audio-in" to make loading ZX80 tape files easier
2015-04-09	9	9	1	Crash	Taperecorder	instand load crashed at end of tape if tape was "running"
2015-04-09	8	8	1	Bug	Inves	could not load from tape recorder
2015-04-08	0.6	3	5	Todo	Inspector	rework managment of custom window title for TapeRecorder and DivIDE
2015-04-09	4.5	9	2	Crash	FDC	crash when accessing beyond allocated tracks, e.g. on empty side
2012-09-30	2.25	9	4	Todo	Tape	ZX80 instant save
2012-09-30	2.25	9	4	Todo	Tape	ZX81 instant save
2012-09-09	2.25	9	4	Todo	Tape	ZXSP++ instant save
2014-03-28	2.25	9	4	Crash	Tape	save tape in realtime broken, crashes in CswBuffer decoding
2012-10-10	2	8	4	Todo	Tape	Jup Ace: save and instant save
2012-09-30	0.625	5	8	Todo	Tape	ZX80++ O80Data -> CswBuffer -> O80Data ((and P81Data))
2015-01-01	0.1	8	80	Todo	Tape	rework taperecorder, tapefile, tapefiledatablock and tapedata and childs
2014-02-01	0.05	4	80	New	Files	SDCC C Compiler
2015-04-15	1	4	4	Todo	Tape	Play sound while tape is playing
2012-10-18	1	4	4	Todo	Qt	Qt-Abhängigkeit in Uni eliminieren: Item.TapeRecorder
2015-04-18			261			released 0.8.0pre25
2013-10-21	0.1	8	80	New	Item	Currah µSpeech
2015-04-26			80			released 0.8.0pre26
2015-04-30	8	8	1	Bug	.z80	loading .z80 file: SPECTRA bits were taken from wrong byte :-/
2015-05-02	6	6	1	Bug	Z80	noreadpage and nowritepage can no longer be static wg. memory mapped i/o
2012-08-18	0.5	8	16	New	Item	Multiface 1
2012-08-18	1	8	8	New	Item	Multiface 128
2012-08-18	1	8	8	New	Item	Multiface 3
2015-05-18	4	8	2	Bug	Tape	blocks were not split when save "normally", resulting .tap file unusable
2015-05-18			36			released 0.8.0pre27
2016-02-10	3	3	1	Bug	.z80	v2.01++: load uncompressed pages (flag: len=0xffff)
2016-02-10	3	3	1	Bug	.tzx	Block 0x24 LOOP START: ptr not set to NULL in ctor
2016-02-11	3.5	7	2	Bug	128/+2A/+3	lock mmu port does not lock to 48k mode!
2014-04-05	0.5	8	16	Todo	Joystick	implement Keyboard Joystick
2016-02-15	0.0625	1	16	New	Appearance	new dialog boxes
2016-02-15	0.5	1	2	New	.z80	if saving a locked 128/+2/+3: save only accessible ram pages
2016-02-17	0.75	3	4	Todo	Files	remember used filter in file dialog
2016-02-15	0.25	5	20	New	Pentagon	Pentagon 128: noch ohne FDC
2016-02-23	0.5	1	2	ToDo	Keyboard	L-shaped ENTER key
2016-02-25	1	8	8	Bug	+2A/+3	wait cycle style Amstrad != Sinclair
2016-02-25	0.5	2	4	Fix	.z80	create .z80 files with full-size header. Other emulators are soo stupid... :-)
2016-02-28	1.25	5	4	Fix	Memory	write_2x ohne Flag immer ausführen, wenn page.core_2x vorhanden
2016-03-03	2.5	5	2	Fix	Machine	Video Beam Indicator war disfunct
2013-06-13	0.2	8	40	New	File	New File Format: RZX
						Recreated ZX Bluetooth Keyboard
						Refactoring (slots, log, assert, white space, clean-up)
						ToolWindow handling
						fixed flashing gif screenshot
						reworked Currah µSpeech (thx to Thomas Busse)
						fixed index error in FloppyDisk::read_extended_dsk_file
						improved handling of floating bus when reading unmapped memory
						fixed text position in tape recorder counters
						reworked setting speed from speed menu
						fixed openGL error and crashing in ~QPainter in Qt 5.9

## Aktuell
9	App beenden Crash: machine.power_on oder so
9	record .rzx
8	Keyboard Joystick nicht defaultmäßig anklemmen
5	Spectra128 -> Window Menü: DualScreen -> ToolWindow
5	Joystick Overlay
	rzx encoder: snapshot startet mit INT => Leerframe!
	Option: switch to REC at end of PLAY
	Speed menu not updated properly for new machine / loadSnapshot
	Overlay timeline
	Overlay single step

2	read .szx
1	write .szx